# Checklist for Indoor exercise with deployment of means

## Analysis Phase

| TASK | CHECK | Comments | Date |
| --- | --- | --- | --- |
| Identify training needs |  |  |  |
| Identify target group |  |  |  |
| Set Overall Aim |  |  |  |
| Analysis of reference documentation. |  |  |  |
| Review documentation from former or similar actions (including lessons learnt) |  |  |  |
| Set responsible for design phase |  |  |  |
| Identify the type of training that will be developed (seminar, workshop or exercise) |  |  |  |
| Indoor or outdoor training |  |  |  |
| Determine if it will be required to deploy specific resources (vehicles, marine pollution combat resources, communication resources, technical resources, simulators, models, etc.) |  |  |  |

Suggestion: It is recommended that analysis meetings be held with the frequency and periodicity that are necessary to complete the tasks of this phase.

## Design phase:

| TASK | CHECK | Comments | Date |
| --- | --- | --- | --- |
| Consider topics covered and lessons learnt from former actions |  |  |  |
| Set general objectives |  |  |  |
| Establish exercise scope |  |  |  |
| Establish the working team for the design phase. Roles and responsibilities |  |  |  |
| Establish the plan to be developed: |  |  |  |
| Exercise Type |  |  |  |
| Participant Organizations (groups, departments) and roles |  |  |  |
| Number of participants (trainees) |  |  |  |
| Duration |  |  |  |
| Date/s |  |  |  |
| Location/s |  |  |  |
| Budget (financial issues) |  |  |  |
| Other parameters |  |  |  |
| Take into consideration the reuse of materials from former or similar actions. |  |  |  |
| Action plan: |  |  |  |
| Schedule (Actions for the following phases including meetings and deadlines) |  |  |  |
| Operational communications plan (both for participants and staff) |  |  |  |
| Monitoring and evaluation plan (learning and process assessment) |  |  |  |
| Resources: |  |  |  |
| Identification of Means to be deployed. i.e.: vehicles (air, sea, land, etc.), containment and recovery pollution equipment, technical means (simulators, models, laptops, etc.) |  |  |  |
| Human resources (Roles and responsibilities. Both from operational and management perspective) | Air |  |  |
| Facilities (including meeting rooms) |  |  |  |
| Services for participants (transport, accommodation, access, parking, food and refreshments) |  |  |  |
| Information and Communication Technologies (devices, hardware, software and Personal devices requested from participants) |  |  |  |
| Identifications (personal, roles and/or locations) |  |  |  |
| Other resources |  |  |  |
| Legal and administrative considerations: |  |  |  |
| Safety and Health. PPE (Personal protective equipment) |  |  |  |
| GDPR (General Data Protection Regulation) |  |  |  |
| Civil Liability |  |  |  |
| Authorizations/ Notifications |  |  |  |
| Certifications |  |  |  |
| Confidentiality |  |  |  |
| Media and public relations plan |  |  |  |
| Obtain approval from senior manager |  |  |  |

## Development phase:

| TASK | CHECK | Comments | Date |
| --- | --- | --- | --- |
| Establish coordination team (development phase) |  |  |  |
| Determine the coordination and implementation plan for the management of the activity |  |  |  |
| Preparatory meetings |  |  |  |
| Previous visits to the exercise area |  |  |  |
| Confirm the availability of other Organizations/groups involved |  |  |  |
| Develop the exercise programme (overall timing and activities) |  |  |  |
| Develop the exercise scenario and documentation: |  |  |  |
| Timeline and Storyboard (actions) for instructors. |  |  |  |
| Injects for instructors. |  |  |  |
| In case of using simulators, develop the virtual scenario |  |  |  |
| Roles and responsibilities (Trainees and instructors) |  |  |  |
| Support documentation to be used for trainees during Implementation phase: - Site Charts/map. - Forecast/Backwards Model outputs - Weather observation and forecast - Vulnerability maps - List of resources to be deployed and description. - Product data sheet - Vessel/installation….plans - Others |  |  |  |
| Ensure that logistic issues have been addressed: |  |  |  |
| Mandatory roles for the proper development of the exercise are confirmed |  |  |  |
| Own and external Means to be deployed |  |  |  |
| Facilities (including meeting rooms, transport…) |  |  |  |
| Services (transport, accommodation, access, parking, food and refreshments) |  |  |  |
| Information and Communication Technologies |  |  |  |
| Request to bring Personal equipment. |  |  |  |
| Identifications (personal, roles and/or locations) |  |  |  |
| Other resources |  |  |  |
| Develop the Operational communications plan: |  |  |  |
| List of means for communications, access credentials and passwords, and roles associated |  |  |  |
| Official channels for communications and roles associated |  |  |  |
| List of Safety Code Words for the exercise (start, end, cancelled, etc.) |  |  |  |
| Develop or adapt needed documentation: |  |  |  |
| Reports to be sent to participants before the exercise. |  |  |  |
| Briefing and debriefing documents |  |  |  |
| Presentations |  |  |  |
| Checklists |  |  |  |
| Signature list for participants |  |  |  |
| Protocols and handling instructions for equipment |  |  |  |
| Legal forms to be signed |  |  |  |
| Legal considerations. Ensure you have sent the request and you have received: |  |  |  |
| Legal forms signed |  |  |  |
| Information from participants (i.e., personal data to have authorization to access a port or vessel) |  |  |  |
| Ensure that contingencies have been addressed and the information included in the pre-exercise report: |  |  |  |
| Inclement weather |  |  |  |
| Major or live incidents |  |  |  |
| Major communications failure |  |  |  |
| Media and Public Relations plan: |  |  |  |
| Save the date |  |  |  |
| Common guidelines for communications |  |  |  |
| Press releases |  |  |  |
| Verify specific needs for the attendance of Media (transport, specific timetables, etc.) |  |  |  |
| Appoint personnel to record the exercise (pictures, videos, etc.) |  |  |  |
| Invitations |  |  |  |
| Others |  |  |  |
| Monitoring and evaluation plan: |  |  |  |
| Dashboard |  |  |  |
| Checklist |  |  |  |
| Evaluation forms |  |  |  |
| Report format |  |  |  |
| Other monitoring and evaluation documentation |  |  |  |
| Other documentation |  |  |  |
| Previous training: |  |  |  |
| Prepare training and related activities (needed to develop the exercise) |  |  |  |
| Train the exercise trainers |  |  |  |
| Battery of tests (Software, resources, means, equipment, scenario…) |  |  |  |

## Implementation/Conduction phase

| TASK | CHECK | Comments | Date |
| --- | --- | --- | --- |
| Sent pre-exercise reports to participants |  |  |  |
| Sent former documentation (notifications, press release, etc.) |  |  |  |
| Management team briefing/meeting: Review the entire exercise (scenario, documentation, equipment, functions, flow of information, distribution…) |  |  |  |
| Prepare and tests technical resources and equipment |  |  |  |
| Briefing for participants: - Review the exercise: Role responsibilities, actions involved, timing …) - Schedule, timing, and programme - Distribute documentation |  |  |  |
| Familiarisation with equipment, installations, etc. |  |  |  |
| Identification of participants |  |  |  |
| Implement the exercise |  |  |  |
| Monitoring: observe and collect for evaluation |  |  |  |
| Ensure access and information of the Services (access, parking, food and refreshments) to participants |  |  |  |
| After the exercise: |  |  |  |
| Hot wash / Briefing |  |  |  |
| Delivery and collect evaluation forms (participants) |  |  |  |

## Evaluation phase

| TASK | CHECK | Comments | Date |
| --- | --- | --- | --- |
| Analyse collected data (evaluation forms and monitoring data) |  |  |  |
| Assess trainees performance (identify good practices and improvement areas) |  |  |  |
| Develop the exercise report |  |  |  |
| Make recommendations for trainees / organizations (good practices maintenance and itinerary of activities for improvement) |  |  |  |
| Establish learnt lessons for future activities/exercises |  |  |  |
| Prepare a clear and concise summary report |  |  |  |
| Distribute the exercise report or the summary (including press release and gratitude). |  |  |  |

Suggestions to fulfil the box:  Done   Not applicable

Done   Not aplicable